JAPAN - INDONESIA JOINT CALL FOR PROPOSALS on “BIOENERGY”

JST - BRIN NEXUS 2026

Supporting Annexes: Figures, Equations, Implementation Schedule, Research Roadmap, Budget Proposal, and Detailed Budget Plan (RAB)

Proton-Selective Fluorine-Free Composite Membranes for Microbial Electrolysis Cells: Converting Organic Waste into High-Purity Biohydrogen

This document collects the illustrations, governing equations, and the four detailed planning sections (implementation schedule, research roadmap, budget proposal, and detailed budget plan) that support the Joint Application Form (Nexus_Indonesia_Form2026). The tables and figures are consistent with Parts III-V of the form. Equations are reproduced from the source membrane study (J. Membr. Sci. 540 (2017) 165-173).

# 1.  Concept, Working Principle, and Governing Equations

## 1.1  Graphical abstract

The joint concept couples molecular dynamics on the Japan side with membrane fabrication and microbial-electrolysis-cell (MEC) experiments on the Indonesia side. The Japanese team simulates proton and cation transport through the SPAES coarse-grained membrane; the Indonesian team fabricates the SPAES/PIN composite and demonstrates biohydrogen production in the MEC. Predictions and measurements are exchanged in a closed loop.

[ IMAGE PLACEHOLDER ] Figure 1. Combined graphical abstract - Japan side (molecular dynamics simulation; SPAES coarse-grained membrane) and Indonesia side (MEC experimental setup and SPAES/PIN fabrication) feeding the MEC reaction. Source of membrane concept: doi.org/10.1016/j.memsci.2017.06.048 Drop image file here: Proposal/Nexus/images/01_graphical_abstract.png

Figure 1. Graphical abstract of the joint research.

## 1.2  Working principle of the MEC

In the microbial electrolysis cell, exoelectrogenic bacteria at the anode oxidise the organic substrate to protons, electrons, and carbon dioxide. With a small applied voltage (about 1 V shown), electrons reach the cathode through the external circuit and protons migrate across the SPAES/PIN membrane, recombining at the cathode to form hydrogen. Competing cations (Na⁺, K⁺) also cross the membrane and must be rejected relative to protons. The half-reactions are:

[ IMAGE PLACEHOLDER ] Figure 2. MEC working principle at 1 V: anode (substrate → CO2 + H+), cathode (2H2O → H2 + OH-), reference electrodes, and transport of H+ vs Na+/K+ across the SPAES/PIN membrane. Drop image file here: Proposal/Nexus/images/02_mec_reaction.png

Figure 2. Reaction scheme and selective proton transport across the SPAES/PIN membrane.

Anode:  CH3COOH + 2H2O → 2CO2 + 8H+ + 8e−      E° = −0.28 V (NHE)          (1)

Cathode:  8H+ + 8e− → 4H2      E° = −0.42 V (NHE)                       (2)

## 1.3  MEC experimental setup

The two-chamber MEC is operated with substrate feed, HCl dosing under pH control, and effluent and gas-measurement lines. Anode and cathode potentials, pH, and temperature are logged through a National Instruments data-acquisition (NI DAQ) system, and the electrolyte is recirculated. This instrumentation gives the controlled, monitored conditions required to benchmark the membrane.

[ IMAGE PLACEHOLDER ] Figure 3. MEC experimental setup: reactor with membrane/anode/cathode, effluent and gas-measurement lines, substrate and HCl pumps, recirculation, pH controller, and NI DAQ logging anode/cathode potentials, pH and temperature. Drop image file here: Proposal/Nexus/images/03_mec_setup.png

Figure 3. Instrumented two-chamber MEC test rig.

## 1.4  MEC cell assembly

The cell is a clamped stack: an anode block housing the carbon-felt anode, a membrane gasket holding the SPAES/PIN membrane, and a cathode block housing the titanium/platinum (Ti/Pt) cathode. This exploded view defines the electrode materials and the membrane's central, load-bearing position.

[ IMAGE PLACEHOLDER ] Figure 4. Exploded view of the MEC cell: Anode Block, Anode (carbon felt), Membrane Gasket (SPAES/PIN), Cathode (Ti/Pt), and Cathode Block. Drop image file here: Proposal/Nexus/images/04_cell_assembly.png

Figure 4. MEC cell assembly and electrode materials.

## 1.5  SPAES/PIN membrane fabrication

Polyimide nanofibres (PIN, ~200 nm) are produced by electrospinning to form a mechanical support web. A proton-conducting SPAES solution in N,N-dimethylacetamide (DMAc) is prepared and impregnated into the PIN web; the composite is formed by doctor blading, then dried at 80 °C for 6 h and acidified in 1 N H₂SO₄. The result is a composite in which the SPAES layer conducts protons while the embedded PIN carries mechanical load.

[ IMAGE PLACEHOLDER ] Figure 5. SPAES/PIN fabrication route: PIN electrospinning → SPAES/DMAc solution → impregnation → doctor blading → drying (80 C, 6 h) and acidification (1 N H2SO4) → SPAES/PIN composite (SPAES proton-conductor layer + PIN mechanical supporter). Source: doi.org/10.1016/j.memsci.2017.06.048 Drop image file here: Proposal/Nexus/images/05_membrane_fabrication.png

Figure 5. Fabrication procedure and structure of the SPAES/PIN composite membrane.

## 1.6  Membrane characterization - governing equations

Membrane properties are quantified with the following relations from the source study, where W, A, and T are weight, area, and thickness in the wet and dry states; V and C are the consumed volume and concentration of NaOH; Em is the potential difference; F, R, and T are the Faraday constant, gas constant, and absolute temperature; and C₁, C₂ are the two HCl concentrations:

Water uptake:   WU (%) = ( Wwet − Wdry ) / Wdry × 100                         (3)

Area swelling:   ΔA (%) = ( Awet − Adry ) / Adry × 100                          (4)

Thickness swelling:   ΔT (%) = ( Twet − Tdry ) / Tdry × 100               (5)

Ion exchange capacity:   IEC (meq/g) = ( VNaOH × CNaOH ) / Wdry       (6)

Proton transport number:   t+ = ½ { [ Em·F / ( R·T·ln(C1/C2) ) ] + 1 }     (7)

Baseline targets from the source study that the model must reproduce and the optimization must beat: t₊ = 0.96 (vs 0.91 for Nafion-211); 3-10-fold lower cation crossover; 2-2.5-fold lower gas permeability; tensile strength > 40 MPa; water uptake 35 ± 3 %; IEC 2.3 ± 0.3 meq/g; MEC hydrogen production 32.4 % higher with 90.3 % purity (vs 61.8 %).

# 2.  Implementation Schedule

The 36-month common work plan (fiscal years 2027-2029) is summarised as a quarterly Gantt chart. Japanese (JP) molecular-dynamics work packages, Indonesian (ID) experimental work packages, and joint exchange (EX) activities are shown together so that the predict-verify handovers between the teams are visible. “X” marks an active quarter.

| Work package (JP=Japan, ID=Indonesia, EX=exchange) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| JP1 Build & benchmark GPU-HPC MD platform | X | X |  |  |  |  |  |  |  |  |  |  |
| JP2 Baseline atomistic SPAES model + first MD |  | X | X | X |  |  |  |  |  |  |  |  |
| JP3 EVB/MS-EVB module; DFT-MD validation |  |  | X | X | X |  |  |  |  |  |  |  |
| JP4 Mechanistic model: t+ & cation PMF |  |  |  |  | X | X | X |  |  |  |  |  |
| JP5 Continuum NP/PB fit; design screening |  |  |  |  |  | X | X | X | X | X |  |  |
| JP6 Design map, blind predictions, publish |  |  |  |  |  |  |  |  | X | X | X | X |
| ID1 Upgrade characterization (SAXS/TEM/PALS) | X | X |  |  |  |  |  |  |  |  |  |  |
| ID2 Baseline fabrication & measurement |  | X | X | X |  |  |  |  |  |  |  |  |
| ID3 First DS/IEC family synthesis |  |  | X | X | X |  |  |  |  |  |  |  |
| ID4 Waste-feedstock characterization |  | X | X | X |  |  |  |  |  |  |  |  |
| ID5 Full family characterization (validate) |  |  |  |  | X | X | X |  |  |  |  |  |
| ID6 Side-chain synthesis routes |  |  |  |  |  | X | X | X |  |  |  |  |
| ID7 MEC rig commissioning & acetate baseline |  |  |  |  |  |  | X | X | X |  |  |  |
| ID8 Optimum synthesis & blind validation |  |  |  |  |  |  |  |  | X | X | X |  |
| ID9 Real-waste MEC demonstration & durability |  |  |  |  |  |  |  |  |  | X | X | X |
| ID10 Data deposition & joint IP filing |  |  |  |  |  |  |  |  |  |  |  | X |
| EX ECR doctoral study at Tohoku (continuous) | X | X | X | X | X | X | X | X | X | X | X | X |
| EX Joint Workshops 1/2/3 (Sendai/Bogor/Sendai) |  |  |  | X |  |  |  | X |  |  |  | X |
| EX Reciprocal visits & conference talks |  |  | X | X |  |  | X | X |  |  | X | X |
| EX Joint publications & annual reporting |  |  |  |  |  |  |  | X |  |  |  | X |

Table A1. Quarterly implementation schedule over 36 months. Columns 1-4 = FY2027, 5-8 = FY2028, 9-12 = FY2029. Each year closes with a bidirectional handover.

# 3.  Research Roadmap

The roadmap places the funded 36-month project within a longer trajectory from validated membrane design to domestic manufacture and regional deployment.

## Figure B1.  Ten-year research roadmap

| Phase | Focus |
| --- | --- |
| Phase 1 (2027-2029) — THIS PROJECT | Validated MD structure-selectivity design rule (Gap 1) and an optimized DS/IEC membrane (Gap 2); the blind-tested optimum demonstrated in an MEC on real Indonesian waste versus Nafion-211. |
| Phase 2 (2030-2032) | Scale-up from coupons to continuously cast sheet; pilot MEC on palm oil mill / food-processing effluent; establish a domestic membrane fabrication route. |
| Phase 3 (2033-2036) | Field deployment at agro-industrial sites; extend the platform to microbial fuel cells, reverse electrodialysis, and water treatment; disseminate across ASEAN Member States. |

Figure B1. Ten-year roadmap positioning model-guided, fluorine-free membrane design as a scalable route to a domestically manufacturable bioenergy technology.

## Figure B2.  Three-year research plan (funded project)

| Year | Activities |
| --- | --- |
| Year 1 (FY2027) | Japan builds/benchmarks the MD-HPC platform and the baseline SPAES model; Indonesia upgrades characterization (SAXS/TEM/PALS), reproduces the baseline, synthesises the first DS/IEC family, and characterises the waste feedstocks. Handover both ways. |
| Year 2 (FY2028) | Japan completes and first-validates the mechanistic model (t+, cation crossover from geometry) and begins DS/IEC + side-chain screening; Indonesia validates the family, establishes side-chain routes, and commissions the MEC rigs. First joint publication. |
| Year 3 (FY2029) | Japan finalises the design map and issues blind predictions; Indonesia synthesises the optimum, runs the blind validation, and demonstrates it in real-waste MEC operation; joint IP filing and reporting. |

Figure B2. Three-year plan progressing from baselines, through a validated model and design map, to a blind-tested optimum demonstrated on real Indonesian waste.

# 4.  Budget Proposal

Under the no-cross-border-funding rule, the Japan side is funded by JST in Japanese Yen (Part IV) and the Indonesia side by BRIN/LPDP in Indonesian Rupiah (Part V); the two are budgeted and reported separately. The summaries below match Parts IV-V of the form.

## Table C1.  Japan-side funding summary (1,000 JPY) - funded by JST

| Category | FY2027 | FY2028 | FY2029 | TOTAL (a) | Exchange (b) |
| --- | --- | --- | --- | --- | --- |
| Facilities and equipment | 20,000 | 6,000 | 4,000 | 30,000 | - |
| Consumables | 3,000 | 3,000 | 3,000 | 9,000 | - |
| Travel | 8,000 | 9,000 | 8,000 | 25,000 | 20,000 |
| Personnel | 6,000 | 7,000 | 7,000 | 20,000 | 4,000 |
| Others | 2,000 | 2,000 | 2,000 | 6,000 | 3,000 |
| Direct total (a) | 39,000 | 27,000 | 24,000 | 90,000 | 27,000 |
| Capacity building (3 ECR) | 11,700 | 11,700 | 11,700 | 35,100 | - |

Table C1. Exchange plan (b) = 27,000 = 30.0% of direct (a). Indirect = 30% of direct, added separately by JST. Capacity building: 3.9M JPY/ECR/year, 11.7M/ECR maximum.

## Table C2.  Indonesia-side funding summary (1,000 IDR) - funded by BRIN/LPDP

| Category | FY2027 | FY2028 | FY2029 | TOTAL |
| --- | --- | --- | --- | --- |
| Direct - Personnel (<=25%) | 240,000 | 240,000 | 240,000 | 720,000 |
| Direct - Consumables | 380,000 | 400,000 | 370,000 | 1,150,000 |
| Direct - Travel | 90,000 | 95,000 | 100,000 | 285,000 |
| Direct - Capital (<=10%) | 95,000 | 60,000 | 40,000 | 195,000 |
| Direct - Others | 145,000 | 155,000 | 200,000 | 500,000 |
| Indirect (<=5%) | 50,000 | 50,000 | 50,000 | 150,000 |
| TOTAL (<= Rp 1,000,000/year) | 1,000,000 | 1,000,000 | 1,000,000 | 3,000,000 |

Table C2. Checks: personnel 24.0% (<25%); capital 6.5% (<10%); indirect 5.0% (<5%); annual request Rp 1 billion; duration 36 months - all within BRIN limits.

# 5.  Detailed Budget Plan (RAB) - Indonesia Side

The RAB required by BRIN itemises the Indonesia-side (Rupiah) budget only; the Japan-side budget is in Part IV (Yen) and no cross-border funding is used. MD/HPC and all software licences are therefore absent here (Japan-side costs). Amounts are in thousand Rupiah (1,000 IDR); 3-year totals.

Title: Proton-Selective Fluorine-Free Composite Membranes for MECs - Converting Organic Waste into High-Purity Biohydrogen

Scheme: JST-BRIN NEXUS Joint Call 2026 (Bioenergy) / RIIM Kolaborasi     Indonesia PI: Prof. Nasruddin (Universitas Indonesia)

Co-PI / Team: Dr.Eng. Obie Farobie, M.Si. (IPB University); Erdiyanto Munandar (BRIN)

## Budget Summary (Recapitulation)

| Description | Cost (1,000 IDR) |
| --- | --- |
| Personnel (max 25%) | 720,000 |
| Consumables | 1,150,000 |
| Travel | 285,000 |
| Capital (max 10%) | 195,000 |
| Other Operational Costs | 500,000 |
| Indirect / Monitoring & Evaluation (max 5%) | 150,000 |
| TOTAL (3 years) | 3,000,000 |

## Detailed Breakdown (3-year totals, 1,000 IDR)

A. Personnel

| Item (name / series / origin) | Justification | 3-yr (Rp) |
| --- | --- | --- |
| Research team honoraria (PI/Co-PI/researcher/students) | Team member honoraria, held below the 25% ceiling. | 540,000 |
| Field workers (waste sampling) | Feedstock sampling campaign. | 120,000 |
| Expert fees | Membrane/bioprocess expertise. | 60,000 |
| SUBTOTAL |  | 720,000 |

B. Consumables (experiment)

| Item (name / series / origin) | Justification | 3-yr (Rp) |
| --- | --- | --- |
| SPAES base resin (Kolon, South Korea) + DS/IEC synthesis reagents | Base resin + reagents for the membrane family. | 250,000 |
| Side-chain modifiers (hydroxyl; n-BuOH) | Channel-narrowing modification routes (Gap 2). | 120,000 |
| N,N-dimethylacetamide (DMAc) | Casting solvent for SPAES. | 60,000 |
| Polyimide precursor + electrospinning consumables (~200 nm) | Electrospun PIN mechanical support. | 120,000 |
| Nafion-211 (DuPont, USA) | Benchmark control membrane. | 60,000 |
| Chemicals (H2SO4, NaCl, NaOH, HCl, phenolphthalein, std cations) | Acidification, IEC titration, crossover. | 90,000 |
| Nitrogen (99.999%) & standard gas | Carrier gas & gas-crossover analysis. | 60,000 |
| MEC electrode materials: carbon felt anode; Ti/Pt cathode | Anode & cathode + VFA substrate. | 120,000 |
| SAXS measurement time (contracted) | Channel width & cluster spacing. | 120,000 |
| TEM tomography time (contracted) | 3D tortuosity & connectivity. | 100,000 |
| PALS measurement time (contracted) | Free-volume / void size. | 50,000 |
| SUBTOTAL |  | 1,150,000 |

C. Travel

| Item (name / series / origin) | Justification | 3-yr (Rp) |
| --- | --- | --- |
| Domestic travel (feedstock sampling, IPB-UI, dissemination) | Coordination & national dissemination (Rp 30M/yr). | 90,000 |
| International travel - data & joint analysis (Tohoku); <=10% cap | Joint analysis at Tohoku (Rp 60/65/70M, FY27-29). | 195,000 |
| SUBTOTAL |  | 285,000 |

D. Capital (instrumentation; name / series / origin) - <=10%

| Item (name / series / origin) | Justification | 3-yr (Rp) |
| --- | --- | --- |
| Data-acquisition multimeter (Keithley 2700 series, USA) | Proton transport number (t+) measurement. | 60,000 |
| Ag/AgCl reference electrodes (Microelectrode, USA) | Reference for t+ cell (+0.195 V vs NHE). | 20,000 |
| Gastight syringes (Hamilton SampleLock #1002, 2.5 mL, USA) | MEC headspace gas sampling. | 15,000 |
| Electrospinning unit hardware | PIN fabrication (~200 nm). | 60,000 |
| Two-chamber MEC reactor hardware (180 mL) | Biohydrogen MEC operation (0.5 V). | 40,000 |
| SUBTOTAL |  | 195,000 |

E. Other Operational Costs

| Item (name / series / origin) | Justification | 3-yr (Rp) |
| --- | --- | --- |
| Joint Workshop 2 hosting (Indonesia, FY2028) | Convening of the FY2028 joint workshop. | 120,000 |
| Article Processing Charges (APC) | Publication in reputable Q1 international journals. | 150,000 |
| Ethical clearance & foreign research permit processing | Ethics Committee & klirensetik permit. | 40,000 |
| Data deposition (BRIN RIN) | Primary-data repository deposit. | 30,000 |
| Meeting expenses | Project & coordination meetings. | 60,000 |
| Research materials & supplies | Consumable office/research supplies. | 100,000 |
| SUBTOTAL |  | 500,000 |

F. Indirect (Monitoring & Evaluation) - <=5%

| Item (name / series / origin) | Justification | 3-yr (Rp) |
| --- | --- | --- |
| Monitoring & evaluation | M&E by the beneficiary institution (capped at 5%). | 150,000 |
| SUBTOTAL |  | 150,000 |

GRAND TOTAL (Indonesia side, 3 years) = 3,000,000 (1,000 IDR) = Rp 3,000,000,000.

Note: FE-SEM (TESCAN-MIRA3 LMU, Czech) with EDX, AFM (tapping mode), Instron 5967 tension tester (Instron Corp., USA; ASTM D882), ion chromatography (ICS5000, DIONEX, USA), and gas chromatograph (Series 580, GawMac Instrument Co., USA; Porapak Q column) are existing/shared facilities used on a service basis and are not new-purchase items.

Approved,                                                            Bogor, ____ July 2026

Head of Institution / Dean                                Principal Investigator (Indonesia)

Prof. ____________________                          Prof. Nasruddin, Universitas Indonesia